### CLOSE OUT REPORT of UMUECHEM FLOW STATION

#### MECHANICAL FABRICATION OF 8’’ SUCTION,4’’ DISCHARGE HEADEAR, FUEL GAS AND AIR LINE

PROJECT TITLE: - INTERCONNECTING PIPING FOR EP 6 PUMP

Client: HEIRS ENERGIES LIMITED

Contractor: ANBE NIGERIA LIMITED

Location: UMUECHEM FLOW STATION

# INTRODUCTION

This report presents the detailed close-out summary of the Interconnecting Piping for EP-6 Pump Project executed by ANBE Nigeria Limited.

The project scope covered the engineering design, fabrication, installation support activities, Non-Destructive Testing (NDT), hydrotesting, civil support works, electrical/instrumentation connections, and associated mechanical/piping activities required for the successful completion of the EP-6 pump interconnection works.

All fabrication and associated activities were executed in accordance with client specifications, approved engineering standards, applicable codes, and Health, Safety, and Environment (HSE) requirements.

The project was completed successfully without incident, injury, equipment damage, or environmental impact, while maintaining quality and schedule requirements throughout the execution period.

# SCOPE OF WORK

The project execution scope included the following activities:

- Engineering design

- Procurement and supply of required materials

- Site mobilization of personnel, tools, and equipment

- Freedom to Operate (FTO) approvals and compliance

- Mechanical and piping fabrication works

- Civil support activities

- Electrical and Instrumentation (E&I) connections

- Non-Destructive Testing (NDT) activities

- Hydrotesting of fabricated spools

- Surface preparation and coating works

- Pump alignment activities

- Decommissioning & Installation activities

- As-built documentation and reporting

- Site demobilization upon completion

### Mechanical / Piping Works Executed

The mechanical and piping scope specifically included:

    - Engineering design drawings

    - Procurement of mechanical, civil & instrumentation materials

    - Yard fabrication of piping spools

    - FTO

    - Mobilization of personnel, welding machines, tools, and equipment

    - Decommissioning of existing piping spools and support structures

    - Welding and fabrication of seven (7nos) piping spools

    - Welding & fabrication of structural supports

    - Non-Destructive Testing (RT/MPI)

    - Hydrotesting of fabricated 7 no’s piping spools

    - Surface preparation through power brushing

    - Grit blasting.

    - Priming and painting activities

    - Mobilization to site

    - Pump alignment

    - Decommissioning of existing piping’s & supports

    - Installation of newly fabricated piping’s & supports

    - E & I works

    - Exhaust modification

    - Installation of equipment (Civil works foundation, & structural pipe support for pump discharge line)

    - Exhaust cladding.

    - Scaffolding

    - Preparation of as-built drawings and close-out documentation

# WORK SUMMARY EXECUTED

### Mechanical / Piping Activities

| Activity | Quantity / Details |
| --- | --- |
| Mobilization of personnel, equipment, and materials | Lumpsum |
| Freedom to Operate (FTO) | Lumpsum |
| Engineering Design (ISO, model) | Lumpsum |
| Yard fabrication works(piping) | Completed |
| 8” welded joints (butt weld piping) | 8 joints |
| 4” welded joints (butt weld piping) | 10 joints |
| 2” welded joints (butt weld piping) | 12 joints |
| 1” welded joints (butt weld piping) | 12 joints |
| Radiography / RT of welded joints piping’s | 8”-8joints, 4”-10joints, 2”-12joints, 1” -12joints) |
| Yard fabrication works (structural supports) | Completed |
| 1" to 2" Cut out and replace by welding damaged structural members | 27 points (for beam structural support) |
| MPI Testing on fillet weld 1" to 2" Cut out and replace by welding damaged structural members | 27 points (for beam structural support) |
| Hydrotesting of 8”, 4”, 2”, and 1” piping spools | 7 spools (8”-2 spool, 1”- 4”- 5 spools) |
| Grit blasting | 32 sqm |
| Power brushing | 32 sqm |
| Priming and painting | 32 sqm |
| Decommissioning of existing piping structures/spools | Lumpsum |
| Pump Alignment | Lumpsum |
| Installation of piping’s spools | Lumpsum |
| Provision of 10T self-loader | 3 days |
| Cladding of 4” exhaust piping | 4.5 meters |
| Scaffolding | 7.5 sqm |
| Demobilization of Personnel | Lumpsum |
| Preparation of as-built documentation and reports | Lumpsum |

## – Civil Works

| Activity | Quantity / Details |
| --- | --- |
| Demolition of reinforced concrete | 2.10 Each |
| Excavation / carting away of earth on land terrain | 2.10 Each |
| Supply and placement of Grade 15 concrete | 0.20 Each |
| Supply and placement of Grade 30 concrete | 1.00 Each |
| Supply, cutting and fixing of 16 mm reinforcement bars | 200 kg |
| Supply, cutting and fixing of 12 mm reinforcement bars | 200 kg |
| Provision and construction of formwork | 6.10 sqm |
| Provision of approved backfill material, backfilling and compaction | 2.20 Each |
| Installation of anchor bolts (7/8” x 250 mm) | 8 pcs |

## Instrumentation / E&I Activities

| Activity | Quantity / Details |
| --- | --- |
| Installation of equipment & accessories | lumpsum |
| Installation of 3/8” stainless steel tubing for sensing line | 4 pcs |
| Installation of 2” OD unions | 10 pcs |
| Installation of 2” OD elbows | 9 pcs |
| Installation of 2” OD union tee (compression type) | 3 pcs |
| Installation of 3/8” OD unions | 9 pcs |
| Installation of 3/8” OD union tee (compression type) | 3 pcs |
| Installation of 3/8” OD elbows | 2 pcs |
| Installation of 3-Way 1/4” isolation ball valve | 1 pc |
| Installation of 1/4” isolation ball valve | 1 pc |
| Installation of discharge pressure gauge (0–100 Barg) | 1 pc |
| Installation of suction pressure gauge (0–10 Barg) | 1 pcs |
| Installation of sensing line pressure gauge (0–4 Barg) | 1 pc |
| Installation of gauge adapter fittings | 1 pc |
| Installation of needle valves THRD 3000# | 1 pcs |

# LIST OF MATERIALS USED

### Mechanical Works Materials

| S/N | Material Description | Quantity Supplied | Quantity Used | Balance |
| --- | --- | --- | --- | --- |
| 1 | 8” Pipe SCH 80 | 1 Length | Fully Utilized | 0 |
| 2 | 8” 150# RF flange | 4 pcs | Fully Utilized | 0 |
| 3 | 8” 150# RF gasket | 3 pcs | Fully Utilized | 0 |
| 4 | 8” x 45 deg Elbow CS | 2 pcs | Fully Utilized | 0 |
| 5 | 2” Pipe SCH 80 | 2 lenght | Fully Utilized | 0 |
| 6 | U-bolts | 1 pc | Fully Utilized | 0 |
| 7 | 1 inch valve | 1 pc | Fully Utilized | 0 |
| 8 | 4” Pipe SCH 80 | 1 Length | Fully Utilized | 0 |
| 9 | 2” SCH 80 Elbow 90° | 5 pcs | Fully Utilized | 0 |
| 10 | 4” x #600 RFWN Flange | 3 pcs | Fully Utilized | 0 |
| 11 | 2” SCH 80 WN Flange #150 | 1 pc | Fully Utilized | 0 |
| 12 | 4” x #600 RF Gasket | 3 pcs | Fully Utilized | 0 |
| 13 | 4” Elbow 90° SCH 80 | 1 pc | Fully Utilized | 0 |
| 14 | 1” Pipe SCH 80 | 1 Length | Fully Utilized | 0 |
| 15 | 1” Flange x 150 Class | 3 pcs | Fully Utilized | 0 |
| 16 | 2” x 1” Reducer SCH 80 | 1 pc | Fully Utilized | 0 |
| 17 | 1” Elbow 90° SCH 80 | 4 pcs | Fully Utilized | 0 |
| 18 | 2” Gasket x 150 Class | 3 pcs | Fully Utilized | 0 |
| 19 | 1” Gasket x 150 Class | 3 pcs | Fully Utilized | 0 |
| 20 | ½” x 90 mm Bolts and Nuts | 16 pcs | Fully Utilized | 0 |
| 21 | 5/8” x 90 mm Bolts and Nuts | 16 pcs | Fully Utilized | 0 |
| 22 | ¾” x 120 mm Bolts and Nuts | 24 pcs | Fully Utilized | 0 |
| 23 | 7/8” x 150 mm Bolts and Nuts | 24 pcs | Fully Utilized | 0 |
| 24 | Flexible connector for export pump | 1pc | Fully Utilized | 0 |
| 25 | Needle Valves ½” | 2 pcs | Fully Utilized | 0 |
| 26 | ¾” x ½” Reducer | 2 pcs | Fully Utilized | 0 |
| 27 | 4” Elbow 45° | 2 pcs | Fully Utilized | 0 |
| 28 | Modification of 4” Exhaust Pipe | 1 m Pipe | Fully Utilized | 0 |
| 29 | Threadolet 4 x ¾” | 2 pcs | Fully Utilized | 0 |

## Civil Works Materials

| S/N | Material Description | Quantity Supplied | Quantity Used | Balance |
| --- | --- | --- | --- | --- |
| 1 | Demolition of any specified reinforced concrete grade | 2.00 | Fully utilized | 0 |
| 2 | Grade 15 Concrete | 0.30 Each | Fully utilized | 0 |
| 3 | Grade 30 Concrete | 1.10 Each | Fully utilized | 0 |
| 4 | 16 mm High Yield Reinforcement Bars | 206 kg | Fully utilized | 0 |
| 5 | 12 mm High Yield Reinforcement Bars | 206 kg | Fully utilized | 0 |
| 6 | Anchor Bolt – 7/8” x 250 mm | 8 pcs | Fully utilized | 0 |
| 7 | Formwork Materials | 6.40 sqm | Fully utilized | 0 |
| 8 | Backfill Materials | 2.60 Each | Fully utilized | 0 |
| 9 | Excavation / carting away of earth on land terrain | 2.00 | Fully utilized | 0 |

## Instrumentation / E&I Materials

| S/N | Material Description | Quantity Supplied | Quantity Used | Balance |
| --- | --- | --- | --- | --- |
| 1 | 2” OD Union | 12 pcs | Fully utilized | 0 |
| 2 | 2” OD Elbow | 12 pcs | Fully utilized | 0 |
| 3 | 2” OD Union Tee (Compression Type) | 5 pcs | Fully utilized | 0 |
| 4 | 3/8” OD Union | 10 pcs | Fully utilized | 0 |
| 5 | 3/8” OD Union Tee (Compression Type) | 5 pcs | Fully utilized | 0 |
| 6 | 3/8” OD Elbow | 5 pcs | Fully utilized | 0 |
| 7 | 3/8” Stainless Steel Tubing (304/316) | 5 pcs | Fully utilized | 0 |
| 8 | 3-Way 1/4” Isolation Ball Valve, 316 SS | 1 pc | Fully utilized | 0 |
| 9 | 1/4” Isolation Ball Valve, 316 SS | 1 pc | Fully utilized | 0 |
| 10 | Sensing Line Pressure Gauge (0–4 Barg) | 1 pc | Fully utilized | 0 |
| 11 | Discharge Pressure Gauge (0–100 Barg) | 1 pc | Fully utilized | 0 |
| 12 | Suction Pressure Gauge (0–10 Barg) | 2 pcs | Fully utilized | 0 |
| 13 | Gauge Adapter Fittings | 1 pc | Fully utilized | 0 |
| 14 | Needle Valve THRD 3000# (1/2”–1”) | 2 pcs | Fully utilized | 0 |

# HSE PERFORMANCE

### HSE Implementation Measures

The following HSE control measures were implemented throughout the project execution period:

- Daily toolbox meetings conducted before commencement of work

- Continuous monitoring and correction of unsafe acts and conditions

- Deployment of adequate security personnel including JTF and local security teams

- Mandatory use of appropriate Personal Protective Equipment (PPE)

- Availability of first aid equipment onsite

- Job Hazard Analysis (JHA) conducted before and during critical activities

- Permit-to-Work (PTW) system strictly implemented and reviewed daily

- Barricading of work areas to prevent unauthorized access

### HSE Summary

| HSE Activity | Status |
| --- | --- |
| Daily Toolbox Meetings | Completed |
| HSE Inductions | Completed |
| Permit-to-Work Compliance | Maintained |
| Fire Extinguishers Onsite | Available |
| Waste Segregation | Implemented |
| Emergency Drill | Not Conducted |
| Incidents / Accidents | None |

# PROJECT PERSONNEL SUMMARY

| Role | Number |
| --- | --- |
| Project Supervisors | 2 |
| Project Engineer | 1 |
| HSE Officer | 1 |
| Site Nurse | 1 |
| Welders | 1 |
| Mechanical Fitters | 2 |
| Fitters | 2 |
| Total Personnel | 10 |

# EQUIPMENT DEPLOYED

| Equipment | Quantity |
| --- | --- |
| Toolbox | 1 |
| Fire Extinguishers | 2 |
| Crew Box | 2 |
| Self Loader | 1 |

# PROJECT ACHIEVEMENTS

The following milestones were successfully achieved during project execution:

- Successful execution of all mechanical and piping fabrication works in accordance with approved specifications

- Completion of all NDT and QA/QC inspections with satisfactory results

- Successful hydrotesting of all fabricated piping spools

- Timely delivery of project activities within the approved schedule

- Zero Lost Time Injury (LTI) recorded throughout project execution

- Zero environmental incidents and no reported near misses

- Successful completion of coating and surface preparation activities

# CONCLUSION

The Umuechem Interconnecting Piping Works for EP-6 Pump was successfully executed by ANBE Nigeria Limited in full compliance with client specifications, approved engineering standards, and HSE requirements.

All project objectives were achieved safely, efficiently, and within the approved schedule. The successful delivery of the project further demonstrates ANBE Nigeria Limited’s commitment to quality service delivery, operational excellence, and adherence to industry best practices.

DESIGNATION	DESIGNATION

HEL: QAQC SUPERVISOR	ANBE: PROJECT MANAGER

NAME: NELSON AKPUKPULA	NAME: GEORGE HAROLD

SIGNATURE:	SIGNATURE:

DATE:	DATE:11th MAY 2026